## Frontend
OpenModelica Development Status - Frontend
|  | Current Version Last Changed Date: 2011-03-10 | Previous Version Date: 2010-12-03
|  | FILL IN DAYS AND DATE ONLY INTO YELLOW CELLS! | DON'T TOUCH GREY CELLS! |  |  |  |  | FILL THIS FIELD ONLY ONCE
# | Note | Issue | Who | Done? | Status | Original | Days | Days | Days | Date | PrevDate | Description
Spalte1 | Spalte2 | Spalte3 | Spalte4 | Spalte5 | Percent | Estimate | Estimate6 | Done | Remaining | changed | changed7 | Spalte8
4.0 |  | Refactoring |  |  | 100% | 30 | 44.125 | 44.125 | 0
|  | Graphical API support, 80% delivery level (i.e., functionality, not performance) | Adrian | Done | 100% | 6 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
|  | Bug fixing phase 1, 80% delivery level | Adrian | Done | 100% | 6 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
|  | Merging with trunk (updated with new merging hours 2010-06-15) | Adrian | Done | 100% | 6 | 12.125 | 12.125 | 0 | 2010-06-15 | 2010-04-15
|  | Reimplementation of parser to fix missing positions, 80% delivery level | Adrian | Done | 100% | 6 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
|  | Peformance improvement, 80% delivery level | Adrian | Done | 100% | 6 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
|  | Peformance improvement, up to 100% delivery level | Adrian | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
6.0 |  | MultiBody |  |  | 99.92% | 149.225 | 263.275 | 263.075 | 0.2
| i21,i24 | Meetings and coordination (OSMC Development meetings) | Adrian | Done | 100% | 0.1 | 6.125 | 6.125 | 0 | 2010-08-23 | 2010-06-16
|  | Determine if a component is a node in virtual connection graph | Hannu | Done | 100% | 5 | 5 | 5 | 0 | 2010-04-15 | 2010-02-26
|  | Collect information about connections in instantiation | Hannu | Done | 100% | 13 | 13 | 13 | 0 | 2010-04-15 | 2010-02-26
|  | Merging of nodes and break branches | Hannu | Done | 100% | 20 | 20 | 20 | 0 | 2010-04-15 | 2010-02-26
|  | Connections.isRoot (use the list of roots to evaluate expressions) | Hannu | Done | 100% | 5 | 5 | 5 | 0 | 2010-04-15 | 2010-02-26
|  | Connection graph integration with connection sets & testing | Adrian | Done | 100% | 15 | 24.625 | 24.625 | 0 | 2010-04-15 | 2010-02-26
|  | Inner/Outer full support (excluding functions and arrays) | Adrian | Active | 99.69% | 5 | 16.3 | 16.25 | 0.05 | 2010-04-15 | 2010-02-26
| i21 | Inner/Outer performance improvement | Adrian | Done | 100% | 25 | 20 | 20 | 0 | 2010-06-15 | 2010-04-15
| i21 | Improved flattening performance using IOStreams | Adrian | Done | 100% | 2 | 2 | 2 | 0 | 2010-06-15 | 2010-04-15
|  | Adrian help with various issues (Type alias to array type, branch, array iterators, etc) | Adrian | Done | 100% | 5 | 7.5 | 7.5 | 0 | 2010-04-15 | 2010-02-26
|  | Array modifications | Adrian | Done | 100% | 0 | 2.6 | 2.6 | 0 | 2010-04-15 | 2010-02-26
|  | No constant binding for frame_a.R | Adrian | Done | 100% | 0 | 1 | 1 | 0 | 2010-04-15 | 2010-02-26
| i21 | Expandable connectors & testing | Adrian | Done | 100% | 0 | 60.125 | 60.125 | 0 | 2010-10-18 | 2010-08-23
|  | Function call via the World component (gravityAcceleration) | Adrian | Active | 99.61% | 5 | 12.8 | 12.75 | 0.05 | 2010-04-15 | 2010-02-26 | Used in MultiBody: Forces.mo, Joints.mo, parts.mo
|  | Merging, e.g. of bugfixes from bootstrapping branch | Martin | Done | 100% | 0 | 1 | 1 | 0 | 2010-04-15 | 2010-02-26
|  | DLL/SO-generation needed for function-calls in flattening | Per | Done | 100% | 0 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
| i21 | Testing, Debugging and Performance of Multibody flattening | Adrian | Done | 100% | 5 | 12.725 | 12.725 | 0 | 2010-04-15 | 2010-02-26
|  | Test framework and test script improvements | Martin | Done | 100% | 2 | 2 | 2 | 0 | 2010-05-21 | 2010-04-15
|  | Error: Variable eAxis_ia: trying to override final variable | Adrian | Done | 100% | 1 | 0.5 | 0.5 | 0 | 2010-04-15 | 2010-02-26
|  | Error modifier (s) not found in the built-in class Real | Adrian | Done | 100% | 2 | 1.5 | 1.5 | 0 | 2010-04-15 | 2010-02-26
|  | Error: Variable boxBody1.r[1] not found in scope <global scope> | Adrian | Done | 100% | 2 | 1.5 | 1.5 | 0 | 2010-04-15 | 2010-02-26 | https://openmodelica.org:8443/cb/issue/1175
|  | Vectorization of extended types | Per | Done | 100% | 0.1 | 3 | 3 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1119
|  | Sum of arbitrarily sized vector | Per | Done | 100% | 0.1 | 2 | 2 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1153?navigation=true
|  | vector function fix | Per | Done | 100% | 0.1 | 3 | 3 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1164?navigation=true
|  | Determine dimension of variable from function call | Per | Done | 100% | 0.1 | 5 | 5 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1170?navigation=true
|  | Lookup in inherited classes | Alexey | Done | 100% | 0.1 | 3 | 3 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1074?navigation=true
|  | Modification with integer overflow | Alexey | Active | 96.77% | 0.1 | 3.1 | 3 | 0.1 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1074?navigation=true
|  | Incomplete propagation of modifications when using type alias | Per | Done | 100% | 4 | 4 | 4 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1179
|  | Connection breaking via command line + implementation of rooted | Adrian | Done | 100% | 5 | 5.875 | 5.875 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1268
|  | Rewrite connection handling according to Modelica specification | Per | Done | 100% | 14 | 9 | 9 | 0 | 2010-12-03 | 2010-10-18
|  | Rewrite Cevalfunc to use the instantiated DAE instead of Scode | Per | Done | 100% | 12 | 6.5 | 6.5 | 0 | 2010-12-03 | 2010-12-03 | https://openmodelica.org:8443/cb/issue/1333?navigation=true
|  | BUGS #1315 + #1362 | Adrian | Done | 100% | 1.25 | 1.25 | 1.25 | 0 | 2010-12-03 | 2010-12-03 | https://openmodelica.org:8443/cb/issue/1315 | https://openmodelica.org:8443/cb/issue/1362
|  | BUGS #1325 (overconstrained when extends) | Adrian | Done | 100% | 0.375 | 0.375 | 0.375 | 0 | 2010-12-03 | 2010-12-03 | https://openmodelica.org:8443/cb/issue/1325
7.0 |  | Media |  |  | 75.44% | 163.1 | 187.3 | 141.3 | 46
|  | Meetings and coordination (OSMC Development meetings about Media) | Adrian | Done | 100% | 0.1 | 0.5 | 0.5 | 0 | 2010-04-15 | 2010-02-26
|  | Redeclare record/function/model extends X (High Priority) | Martin | Done | 100% | 9 | 6 | 6 | 0 | 2010-04-15 | 2010-02-26
|  | Function inlining annotation (Ruediger Francke: needed for Media)** | Stefan | Done | 100% | 5 | 13.5 | 13.5 | 0 | 2010-04-15 | 2010-02-26
|  | Annotation propagation | Stefan | Active | 50% | 4 | 4 | 2 | 2 | 2010-04-15 | 2010-02-26
|  | Late Function inlining (after index reduction) | ? | Proposed | 0% | 0 | 5 | 0 | 5 | 2010-04-15 | 2010-02-26
|  | Merging, e.g. of bugfixes from bootstrapping branch | Martin | Done | 100% | 3 | 1 | 1 | 0 | 2010-04-15 | 2010-02-26
|  | Lookup in inherited classes fail (from MathCore) | Martin+Alexey | Done | 100% | 2 | 0.2 | 0.2 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1074?navigation=true
|  | Modifiers are not completely implemented (from MathCore) | Alexey | Proposed | 0% | 5 | 5 | 0 | 5 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1065?navigation=true
|  | Code generation of string compare (from MathCore) | ? | Done | 100% | 2 | 0.1 | 0.1 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1054?navigation=true
|  | Lookup of constants from function default parameters | Martin | Active | 66.67% | 4 | 12 | 8 | 4 | 2010-04-15 | 2010-02-26
| i21 | Weird lookup rules only used in Modelica.Media (dependency analysis for functions) | Martin, Adrian | Active | 50% | 10 | 10 | 5 | 5 | 2010-04-29 | 2010-04-15
|  | Unspecified work on Media library | ? | Active | 33.33% | 10 | 12 | 4 | 8 | 2010-04-15 | 2010-02-26
|  | Adding dimensions to Values.ARRAY | Martin | Done | 100% | 2 | 4 | 4 | 0 | 2010-04-15 | 2010-02-26
|  | New instExtends module | Martin | Active | 80% | 25 | 25 | 20 | 5 | 2010-04-15 | 2010-02-26
|  | Reimplementation of function collection (function tree) using the cache | Martin | Done | 100% | 10 | 8 | 8 | 0 | 2010-10-18 | 2010-10-18 | This was needed in order to break infinite loops if certain function calls could not be instantiated
|  | Testing | ? | Active | 0% | 0 | 5 | 0 | 5 | 2010-04-15 | 2010-02-26
|  | Implement Scode-to-SCode to simplify instantiation | Per | Done | 100% | 50 | 50 | 50 | 0 | 2010-03-10 | 2010-12-03 | https://openmodelica.org:8443/cb/issue/1336?navigation=true
|  | Dependency analysis in instElementList | Per | Done | 100% | 3 | 3 | 3 | 0 | 2010-03-10 | 2010-03-10 | http://openmodelica.ida.liu.se:8080/cb/issue/1334
|  | Various fixes for Media | Per | Active | 100% |  | 4 | 4 |  | 2010-03-10 | 2010-03-10
|  | Scode-to-Scode extends (done) and redeclare | Adrian | Active | 63.16% | 19 | 19 | 12 | 7 | 2011-03-11 | 2010-12-07
7.0 |  | Fluid |  |  | 75.69% | 97.75 | 90.5 | 68.5 | 22
|  | Understanding and gathering additional info about stream | ? | Active | 40% | 5 | 5 | 2 | 3 | 2010-04-15 | 2010-02-26
|  | Investigation of the needed compiler changes for stream | ? | Active | 0% | 1 | 1 | 0 | 1 | 2010-04-15 | 2010-02-26
|  | Design sketch of the stream functionality | Adrian | Active | 0% | 2 | 2 | 0 | 2 | 2010-04-15 | 2010-02-26
| I34,35 | Implementation of the stream functionality (connect only) | Adrian | Done | 100% | 15 | 5.75 | 5.75 | 0 | 2010-10-18 | 2010-08-23
|  | Testing of flattening for fluid library | Adrian | Active | 0% | 5 | 5 | 0 | 5 | 2010-04-15 | 2010-02-26
|  | Redeclare construct as element | Adrian | Active | 0% | 1 | 1 | 0 | 1 | 2010-04-15 | 2010-02-26
|  | Functions not inherited correctly when extending packages | Adrian | Active | 0% | 3 | 3 | 0 | 3 | 2010-04-15 | 2010-02-26
|  | Lookup issues and stack overflow | Adrian | Active | 20% | 5 | 5 | 1 | 4 | 2010-04-15 | 2010-02-26
|  | Enumeration type flattening | Adrian | Done | 100% | 18.75 | 18.75 | 18.75 | 0 | 2010-04-15 | 2010-02-26
|  | Record and Record constructors flattening | Adrian | Done | 100% | 5 | 5 | 5 | 0 | 2010-04-15 | 2010-02-26
|  | The new .*,./,.^,.+,.- element-wise operators implementation | Alexey | Done | 100% | 8 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
|  | Unspecified work on Fluid library | ? | Active | 40% | 5 | 5 | 2 | 3 | 2010-04-15 | 2010-02-26
|  | Retain enumeration literals in flattened Modelica code | Per | Done | 100% | 7 | 12 | 12 | 0 | 2010-12-03 | 2010-08-20
|  | Correcting types for expressions | Per | Done | 100% | 10 | 7 | 7 | 0 | 2010-09-10 | 2010-08-20
|  | Testing |  | Proposed | ?? | 0 | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Implement stream connectors | Per | Done | 100% | 7 | 7 | 7 | 0 | 2010-12-03 | 2010-10-18
8.0 |  | Array iterators |  |  | 100% | 40.9 | 27 | 27 | 0
|  | First version of iterator support | Kristian | Done | 100% | 12 | 7 | 7 | 0 | 2010-04-15 | 2010-02-26
|  | Second version, including nested iterators | Alexey | Done | 100% | 12 | 7 | 7 | 0 | 2010-04-15 | 2010-02-26
|  | Range deduction in iterators and for-loops | Alexey | Done | 100% | 11.9 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
|  | Multiple iterators in array constructors and various bugfixes | Per | Done | 100% | 5 | 5 | 5 | 0 | 2010-04-16 | 2010-04-16
9.0 |  | Modelica 3 support |  |  | 71.56% | 44.1 | 53.1 | 38 | 15.1
|  | Modelica 3.0 Balanced models checking | ? | Active | 40% | 18 | 25 | 10 | 15 | 2010-04-15 | 2010-02-26
|  | Items | Alexey | Active | 99.01% | 0.1 | 10.1 | 10 | 0.1 | 2010-04-15 | 2010-02-26
|  | Full Modelica 3.1 flattening support of previously supported Modelica 2.1 libraries | Per | Done | 100% | 26 | 18 | 18 | 0 | 2010-12-03 | 2010-09-10 | http://openmodelica.ida.liu.se:8080/cb/issue/1265
10.0 |  | Speedup of Frontend including Instantiation/Flattening |  |  | 97.88% | 93 | 94.375 | 92.375 | 4.25
|  | Performance enhancement by caching of instantiation functions | Adrian | Active | 87.5% | 2 | 2 | 1.75 | 0.25 | 2010-04-15 | 2010-02-26
|  | MetaModelica/RML changes for performance tracing | Adrian | Active | 106.9% | 14 | 18 | 19.25 | 2 | 2010-10-18 | 2010-08-23
|  | Performance analysis | Adrian | Done | 97.5% | 10 | 10 | 9.75 | 0 | 2010-10-18 | 2010-08-23
|  | Speedup Exp.crefPrefixOf and Exp.crefEqual | Adrian | Active | 86.25% | 20 | 20 | 17.25 | 2 | 2010-10-18 | 2010-08-23
|  | ANTLR3 Parser | Martin | Done | 100% | 5 | 20 | 20 | 0 | 2010-10-18 | 2010-09-10
| i21,i24 | Only perform constant evaluation for structural parameters | Per | Done | 100% | 22 | 7 | 7 | 0 | 2010-04-15 | 2010-02-26 | Only partially done, stalled for now.
|  | Garbage collector for OMC MetaModelica | Adrian | Done | 100% | 20 | 17.375 | 17.375 | 0 | 2010-03-11 | 2010-12-07
11.0 |  | Other Bug fixes |  |  | 98.46% | 66.925 | 65.03 | 64.03 | 1
|  | Problem with [:] in arrays and matrixes | Per | Done | 100% | 3 | 3 | 3 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1146
|  | Fixing getDiagramAnnotation | Per | Done | 100% | 1 | 1 | 1 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1166
|  | Non-constant subscripts in class algorithm sections give erronous error messages | Per | Done | 100% | 4 | 4 | 4 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1180
|  | Lookup problems in the ATplus library | Per | Done | 100% | 4 | 4 | 4 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1151
|  | Instantiation of CombiTable1Ds gives faulty error message | Per | Done | 100% | 2 | 2 | 2 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1187
|  | error messages about division by zero while flattening Bondlib examples | Per | Done | 100% | 2 | 2 | 2 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1186
|  | Function default parameters and unknown dimensions | Per | Done | 100% | 1 | 1 | 1 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1190
|  | Error when final array parameter is set via an initial equation | Per | Done | 100% | 0.5 | 0.5 | 0.5 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1193?navigation=true
|  | Support for loading multiple .mo(f)-files and specifying which class to instantiate | Per | Done | 100% | 0.5 | 0.5 | 0.5 | 0 | 2010-04-16 | 2010-04-16
|  | Final array parameter with fixed=false gives fixed=true when set in initial equation | Per | Done | 100% | 2 | 1 | 1 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1194?navigation=true
|  | elsewhen in equation sections | Jens | Proposed | ?? | ?? | 0 | 0 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1194?navigation=true
|  | Multiple declaration bug | Alexey | Done | 100% | 2 | 2 | 2 | 0 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1071
|  | Multiple class definition bug | Alexey | Active | 80% | 5 | 5 | 4 | 1 | 2010-04-16 | 2010-04-16 | http://openmodelica.ida.liu.se:8080/cb/issue/1182
|  | Detection of nested when-clauses | Per | Done | 100% | 0.15 | 0.15 | 0.15 | 0 | 2010-04-29 | 2010-04-29 | http://openmodelica.ida.liu.se:8080/cb/issue/1189
|  | Disable erronous error messages from Ceval for parameters without bindings | Per | Done | 100% | 1 | 1 | 1 | 0 | 2010-04-29 | 2010-04-29 | http://openmodelica.ida.liu.se:8080/cb/issue/1208 http://openmodelica.ida.liu.se:8080/cb/issue/1212
|  | Elaboration of transpose calls so that the correct variability is used | Per | Done | 100% | 0.15 | 0.15 | 0.15 | 0 | 2010-04-29 | 2010-04-29 | http://openmodelica.ida.liu.se:8080/cb/issue/1210
|  | Fortran77 Code Generation (needed for array dimensions) | Martin | Done | 100% | 1 | 1 | 1 | 0 | 2010-05-21 | 2010-05-21 | https://openmodelica.org:8443/cb/issue/1226
|  | Errors messages: File/Line information virtually everywhere (Static.elabExp) | Martin | Done | 100% | 3 | 3 | 3 | 0 | 2010-10-18 | 2010-10-18
|  | Error messages: Improved for function calls | Martin | Done | 100% | 1.5 | 1.5 | 1.5 | 0 | 2010-10-18 | 2010-10-18
|  | Equality constraint functions has NO inline information | Adrian | Done | 100% | 1 | 0.5 | 0.5 | 0 | 2010-06-15 | 2010-04-15 | https://openmodelica.org:8443/cb/issue/1221
|  | Checking of correct variability in declaration equations | Per | Done | 100% | 2 | 2 | 2 | 0 | 2010-10-18 | 2010-10-18 | http://openmodelica.ida.liu.se:8080/cb/issue/1040
|  | Various enumeration bug fixes | Per | Done | 100% | 2 | 2 | 2 | 0 | 2010-06-15 | 2010-04-15 | https://openmodelica.org:8443/cb/issue/1221
|  | BUG 1285 - Incorrect warning regarding missing 'inner' declaration | Adrian | Done | 100% | 3 | 2.73 | 2.73 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1285
|  | BUG 1264 - report/assign/tests | Adrian | Done | 100% | 1 | 1 | 1 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1264 | https://openmodelica.org:8443/cb/issue/1295 | https://openmodelica.org:8443/cb/issue/1297
|  | BUG 1286 Wrong error message trying to cast from real to integer (debug/test) | Adrian | Done | 100% | 0.5 | 0.5 | 0.5 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1286
|  | BUG 1244, 1295, 1297 | Adrian | Done | 100% | 0.875 | 0.875 | 0.875 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1244 | https://openmodelica.org:8443/cb/issue/1129
|  | BUG 1294 The new parser inserts a CR character before every CRLF in strings | Adrian | Done | 100% | 0.5 | 0.375 | 0.375 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1294 | https://openmodelica.org:8443/cb/issue/1071
|  | BUG 1122, 1129 - Balancing in Modelica.Electrical.MultiPhase.Examples | Adrian | Done | 100% | 1.25 | 1.25 | 1.25 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1122 | https://openmodelica.org:8443/cb/issue/1305
|  | BUG 1234, 1071 - Multiple declarations and BioChem models | Adrian | Done | 100% | 1.125 | 1.125 | 1.125 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1234
|  | BUG 1304, 1305 - String(format), Default values in functions | Adrian | Done | 100% | 0.5 | 0.5 | 0.5 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1304
|  | BUG 1306 Connect clause in parser is not conform to the Modelica specification | Adrian | Done | 100% | 0.125 | 0.125 | 0.125 | 0 | 2010-10-18 | 2010-08-23 | https://openmodelica.org:8443/cb/issue/1304
|  | BUGS 1256,1156,1274,1273,1282,1272,1266 - report/tests/fixes | Adrian | Done | 100% | 2.25 | 2.25 | 2.25 | 0 | 2010-10-18 | 2010-08-23
|  | Bug fixes 2010-12 – 2011-03 | Martin | Done | 100% | 10 | 10 | 10 | 0 | 2011-03-11 | 2011-03-11
|  | Check for components with the same name as their type specifiers | Alexey | Done | 100% | 3 | 3 | 3 | 0 | 2010-10-18 | 2010-10-18
|  | Fix error messages in BioChem models | Adrian, Alexey | Done | 100% | 4 | 4 | 4 | 0 | 2010-10-18 | 2010-10-18 | http://openmodelica.ida.liu.se:8080/cb/issue/1234
|  | BUG #1372, #1367,#1438 | Adrian | Done | 100% | 0 | 10.75 | 10.75 | 0 | 2011-03-11 | 2010-12-07
12.0 |  | Other Issues |  |  | 100% | 82.1875 | 135.5 | 135.5 | 0
|  | OpenProd Meetings | Adrian | Done | 100% | 0 | 2.3125 | 2.3125 | 0 | 2010-06-15 | 2010-04-16
|  | OpenProd Demo (Refactoring) | Adrian | Done | 100% | 0 | 1.375 | 1.375 | 0 | 2010-06-15 | 2010-04-16
| i24 | Installing OpenModelica Build Server | Adrian | Done | 100% | 2 | 1.5 | 1.5 | 0 | 2010-08-23 | 2010-06-15
|  | Non expanded arrays (Frontend part) | Alexey | Active | 100% |  | 30 | 30 |  | 2011-03-11 | 2010-04-15
|  | Non expanded arrays (Meetings with Equa, etc) | Adrian | Done | 100% | 1 | 1 | 1 | 0 | 2010-06-15 | 2010-04-15
|  | Release 1.5.0-RC3 | Adrian | Done | 100% | 1 | 0.625 | 0.625 | 0 | 2010-06-15 | 2010-04-15
|  | Upgrade OpenModelica Server (Svn + MySQL + CodeBeamer + Joomla) | Adrian | Done | 100% | 2 | 6 | 6 | 0 | 2010-08-23 | 2010-08-23
|  | Release 1.5.0-Final | Adrian | Done | 100% | 3 | 5.375 | 5.375 | 0 | 2010-08-23 | 2010-06-15
|  | EOLT Review | Adrian | Done | 100% | 2 | 1.5 | 1.5 | 0 | 2010-08-23 | 2010-06-15
|  | Installation New Laptop + Peter's Laptop | Adrian | Done | 100% | 1 | 1.25 | 1.25 | 0 | 2010-08-23 | 2010-06-15
|  | OpenModelica 1.6.0 release, Bugs | Adrian | Done | 100% | 23.625 | 23.625 | 23.625 | 0 | 2010-12-07 | 2010-10-19
|  | Split FrontEnd/BackEnd, Performance | Adrian | Done | 100% | 15.25 | 17 | 17 | 0 | 2010-12-07 | 2010-10-19
|  | OSX 1.6 Binary Release | Martin | Done | 100% | 2 | 2 | 2 | 0 | 2011-03-11 | 2011-03-11
|  | Administration (Meetings, Server Adm) | Adrian | Done | 100% | 10.1875 | 10.1875 | 10.1875 | 0 | 2010-12-07 | 2010-10-19
|  | Backend week, Others | Adrian | Done | 100% | 13.125 | 13.125 | 13.125 | 0 | 2010-12-07 | 2010-10-19
|  | OpenModelica 1.6.0 release | Adrian | Done | 100% | 0 | 5.125 | 5.125 | 0 | 2011-03-11 | 2010-12-07
|  | Administration (Meetings, Server Adm) 2010-12-07-2011-03-11 | Adrian | Done | 100% | 6 | 6 | 6 | 0 | 2011-03-11 | 2010-12-07
|  | Workshps + Papers Modelica conf + presentations + preparation | Adrian | Done | 100% | 0 | 7.5 | 7.5 | 0 | 2011-03-11 | 2010-12-07

## Backend
OpenModelica Development Status - Backend and Other Things
|  | Current Version Last Changed Date: 2010-06-11 | Previous Version Date: 2010-05-21
|  | FILL IN DAYS AND DATE ONLY INTO YELLOW CELLS! | DON'T TOUCH GREY CELLS! |  |  |  |  | FILL THIS FIELD ONLY ONCE
# | Note | Issue | Who | Done? | Status | Original | Days | Days | Days | Date | PrevDate | Description
| Spalte1 | Spalte2 | Spalte3 | Spalte4 | Percent | Estimate | Estimate5 | Done | Remaining | changed | changed6 | Spalte7
6.0 |  | MultiBody |  |  | 129.2% | 6.125 | 17.125 | 22.125 | 0
|  | DLL/SO-generation | Per | Done | 100% | 0 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
|  | Testing of Multibody simulation | ? | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Vectorization of extended types | Per | Done | 100% | ?? | 3 | 3 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1119
|  | Sum of arbitrarily sized vector | Per | Done | 100% | ?? | 2 | 2 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1153?navigation=true
|  | vector function fix | Per | Done | 100% | ?? | 3 | 3 | 0 | 2010-04-15 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1164?navigation=true
|  | Simulations passing records to functions | Per | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-21 | 2010-02-26
| i21 | Equations assigning function results to records | Jens | Done | ?? | ?? | 0 | 0 | 0 | 2010-05-21 | 2010-05-21
|  | Fixes for world.gravityAcceleration + generation of functions via DAE.FunctionTree | Adrian | Done | 100% | 1.125 | 1.125 | 1.125 | 0 | 2010-08-16 | 2010-06-16
|  | Function derivative annotation | Jens | Done | ?? | 5 | 0 | 5 | 0 | 2010-04-22 | 2010-02-26
7.0 |  | Media |  |  | 50.5% | 7 | 10.1 | 5.1 | 5
|  | Late Function inlining (after index reduction) | ? | Done | 100% | 5 | 5 | 5 | 0 | 2010-04-15 | 2010-02-26
|  | Code generation of string compare (from MathCore) | Alexey | Done | 100% | 2 | 0.1 | 0.1 | 0 | 2010-04-15 | 2010-02-26
|  | fill in | ? | Done | 0% | 0 | 5 | 0 | 5 | 2010-04-15 | 2010-02-26
7.0 |  | Fluid |  |  | 100% | 8 | 8 | 8 | 0
|  | The new .*,./,.^,.+,.- element-wise operators implementation | Alexey | Done | 100% | 8 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
|  | fill in |  | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
8.0 |  | Array iterators |  |  | 100% | 36 | 27 | 27 | 0
|  | First version of iterator support | Kristian | Done | 100% | 12 | 7 | 7 | 0 | 2010-04-15 | 2010-02-26
|  | Second version, including nested iterators | Alexey | Done | 100% | 12 | 7 | 7 | 0 | 2010-04-15 | 2010-02-26
|  | Range deduction in iterators and for-loops | Alexey | Done | 100% | 11.9 | 8 | 8 | 0 | 2010-04-15 | 2010-02-26
|  | Multiple iterators in array constructors and various bugfixes | Per | Done | 100% | 0.1 | 5 | 5 | 0 | 2010-04-15 | 2010-02-26
11.0 |  | Backend Improvements |  |  | 84.41% | 218.5 | 234.125 | 197.625 | 36.5
|  | Meetings, coordination and design of the new Template language | All | Done | 100% | 0.5 | 2.625 | 2.625 | 0 | 2010-04-15 | 2010-02-26
|  | elsewhen in equations | Jens | Done | 100% | 1 | 1 | 1 | 0 | 2010-04-15 | 2010-02-26
|  | Simple tearing algorithm. | Jens | Done | 100% | 30 | 30 | 30 | 0 | 2010-04-15 | 2010-02-26
|  | Relaxation algorthm needed for tearing. | Jens | Done | 100% | 5 | 5 | 5 | 0 | 2010-04-15 | 2010-02-26
|  | Handling division-by-zero including error checking | Jens | Done | 100% | 10 | 10 | 10 | 0 | 2010-04-15 | 2010-02-26
|  | Symbolic Jacobian for ODE-Block with respect to states(x) | Lennart | Done | 100% | 15 | 15 | 15 | 0 | 2010-04-15 | 2010-02-26
|  | Symbolic Jacobian also for algorithm blocks, external functions | Lennart | Done | 100% | 5 | 5 | 5 | 0 | 2010-04-15 | 2010-02-26
|  | Redesign the computing for symbolic Jacobian and implement into trunk | Lennart | Done | 100% | 50 | 50 | 50 | 0 | 2010-10-18 | 2010-02-26
|  | Testing and bugfixes for computing symbolic Jacobian | Lennart, Willi | Done | 100% | 10 | 10 | 10 | 0 | 2010-10-18 | 2010-02-26
|  | Rewrite Linearization and symbolicJacobian in Susan | Lennart, Willi | Done | 0% | 3 | 3 | 0 | 3 | 2010-04-15 | 2010-02-26
|  | Create matrixes BCD for Linearization | Willi | Done | 100% | 3 | 3 | 3 | 0 | 2026-07-29 | 2010-02-26
|  | Event handling for euler method with bisection-Zerocrossing search | Willi | Done | 100% | 15 | 15 | 15 | 0 | 2010-04-15 | 2010-02-26
|  | Event handling for DASSL, set as new default solver | Willi | Done | 100% | 7 | 20 | 20 | 0 | 2026-07-29 | 2010-02-26
|  | Generate linear model | Willi | Done | 100% | 4 | 4 | 4 | 0 | 2026-07-29 | 2010-02-26
|  | Add further implicit solver ( euler implicit) | Willi | Done | 0% | 1 | 1 | 0 | 1 | 2026-07-29 | 2026-07-29
|  | implementation of the built-in operator name homotopy | Lennart | Done | 0% | 15 | 15 | 0 | 15 | 2026-07-29 | 2026-07-29
|  | rewrite all simulation runtime library files | Willi + Lennart | Done | 10% | 10 | 10 | 1 | 9 | 2026-07-29 | 2026-07-29
|  | performance improvements in the generation of the symbolic jacobian | Willi | Done | 20% | 5 | 5 | 1 | 4 | 2026-07-29 | 2026-07-29
|  | improve the usibility of the jacobian matrix | Willi | Done | 0% | 3 | 3 | 0 | 3 | 2026-07-29 | 2026-07-29
|  | C++ solver interface code generation for arrays and external functions | Nicklas | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | New template language based C code generator | Rickard | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | New template language based C# code generator prototype | Pavol | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Leading design and documentation for text template code emission language | PeterF | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Updating template language implementation to new design | Pavol | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Enumerations in backend | Jens | Done | 94.44% | 14 | 9 | 8.5 | 0.5 | 2010-04-15 | 2010-02-26
| i21 | Fortran77 Code Generation (needed for array dimensions) | Martin Per | Done | 100% | 2.5 | 2.5 | 2.5 | 0 | 2010-05-21 | 2010-05-21 | https://openmodelica.org:8443/cb/issue/1226
| i21 | Moving cref name mangling to (template) code generation from backend | Per | Done | 100% | 3.5 | 10 | 10 | 0 | 2010-06-11 | 2010-05-21
| i24 | IOStreams in templates | Martin | Done | 0% | 1 | 1 | 0 | 1 | 2010-06-11 | 2010-06-11
| i24 | Assert/Terminate/etc in runtime | Martin | Done | 100% | 5 | 4 | 4 | 0 | 2011-03-11 | 2010-08-20
|  | basic initial algorithm support | Jens | Done | 100% | 1 | 1 | 1 | 0 | 2010-12-03 | 2010-12-03
|  | interfaces for equation system pipeline | Jens | Active | 100% | 8 | 8 | 8 | 0 | 2011-03-11 | 2010-12-03
|  | fmu export | Azam | Active | ?? | ?? | 0 |  |  | 2011-03-11 | 2010-12-03
|  | fmu import | Wuzhz | Active | ?? | ?? | 0 |  |  | 2011-03-11 | 2010-12-03
12.0 |  | OpenModelica Compiler Bootstrapping |  |  | 100% | 77.2 | 85 | 85 | 0
|  | List support, union types, pattern matching, etc. | Martin | Done | 100% | 0.1 | 28 | 28 | 0 | 2011-03-11 | 2010-12-03
|  | Polymorphic Functions | Martin | Done | 100% | 0.1 | 10 | 10 | 0 | 2010-12-03 | 2010-10-18
|  | Merge and bugfixing of bootstrapping branch into trunk | Martin | Done | 100% | 15 | 9 | 9 | 0 | 2010-10-18 | 2010-04-15
|  | MetaModelica arrays | Martin | Done | 100% | 1 | 1 | 1 | 0 | 2010-04-15 | 2010-02-26
|  | Error messages for expressions | Martin | Done | 100% | 20 | 12 | 12 | 0 | 2010-12-03 | 2010-04-15 | Improved error messages for function calls
|  | Line numbering for the debugger | Martin | Done | 100% | 10 | 10 | 10 | 0 | 2010-10-18 | 2010-08-20
|  | Performance improvement of the bootstrapped compiler, rewriting old compiler | Martin | Done | 100% | 30 | 13 | 13 | 0 | 2011-03-11 | 2011-03-11
|  | Advice on critical issues | Adrian | Done | 100% | 1 | 2 | 2 | 0 | 2010-04-15 | 2010-02-26
13.0 |  | Releases |  |  | 100% | 0 | 2 | 2 | 0
|  | OpenModelica 1.5 beta | Adrian | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | OpenModelica 1.5 | Adrian+Martin | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | OpenModelica 1.5 Mac | Eric(+Martin) | Done | 100% | ?? | 2 | 2 | 0 | 2010-08-20 | 2010-04-15
(Note: Specifications orig estimate=0,1, estimate=0,1, done=0 means that it is not yet specified)
14.0 |  | Other Work |  |  | 100% | 7 | 25 | 25 | 0
|  | Modelica 3.0 annotation support in OMC | Adrian | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Upgrade simForge to support Modelica 3.0 annotations | Filippo | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Non-expanded arrays (backend part) | Kristian? | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Enhancing testsuite for all language constructs in Modelica 3.1 | Stefan | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Integration of sparse solver | Niklas | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | DrModelica enhancement (Mohsen, Stefan) | ? | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | OMNotebook enhancements | ? | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Improving Java Interface | Martin | Done | 100% | 4 | 10 | 10 | 0 | 2010-04-15 | 2010-02-26
|  | Port OpenModelica Interactive to Linux | Per | Done | 100% | ?? | 7 | 7 | 0 | 2010-04-15 | 2010-02-26
|  | Merge OpenModelica Interactive branch with trunk | Per | Done | 100% | 1 | 1 | 1 | 0 | 2010-04-29 | 2010-04-29
|  | Emitting binary simulation data output file in matlab format | Anton | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Cross-platform platform independent build support with CMake | Jens | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | simForge version 0.9 with Modelica 3.1 annotation support | Filippo | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Modelica.Blocks.Tables.CombiTable2D to c_runtime | Jens | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | xxxx | Nicklas | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Ubuntu/Debian binary packages and repository | Martin | Done | 100% | 2 | 2 | 2 | 0 | 2010-04-29 | 2010-04-29
|  | Code generation and constant evaluation of reductions | Per | Done | 100% | ?? | 5 | 5 | 0 | 2010-04-15 | 2010-02-26
|  | New diff tool for Linux/Windows testsuite compatibility | Martin | Done | 100% | 1 | 1 | 1 | 0 | 2010-05-21 | 2010-05-21
|  | Interactive simulation integration | Per, Parham | Done | 100% | 1 | 1 | 1 | 0 | 2010-05-21 | 2010-05-21
|  | CDAC Real-time module integration | Abhi, Per | Done | 0% | 1 | 1 | 0 | 1 | 2010-05-21 | 2010-05-21
|  | Simulate API command needs to show accurate time consumption of subtasks | Martin | Done | 100% | 2 | 2 | 2 | 0 | 2010-10-18 | 2010-09-10
|  | Inline integration (euler/rk) | Martin | Done | 100% | 5 | 5 | 5 | 5 | 2010-08-20 | 2010-08-20
|  | New simulation tests from MSL 2.2.1 | Mohsen, Stefan | Done | 50% | 20 | 20 | 10 | 10 | 2010-05-21 | 2010-05-21
|  | Prefix information in Static error messages | Alexey | Done | 100% | ?? | 4 | 4 | 0 | 2010-12-03 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1235
|  | add more simulation problem from msl to testsuite and get them running | Willi | Done | 26.67% | 30 | 30 | 8 | 22 | 2026-07-29 | 2026-07-29
|  | get the current petrinet library running in OpenModelica | Willi | Done | 50% | 20 | 20 | 10 | 10 | 2026-07-29 | 2026-07-29
15.0 |  | Other Bug fixes |  |  | 100% | 13 | 12.5 | 12.5 | 0
|  | Bug fix example | Adrian | Done | ?? | ?? | 0 | 0 | 0 | 2010-04-15 | 2010-02-26
|  | Fixing Peter Aronssons Changes to functions (MetaModelica, etc) | Martin | Done | 100% | 4 | 4 | 4 | 0 | 2010-04-15 | 2010-02-26
|  | Nested min/max generates code that doesn't compile | Per | Done | 100% | 1 | 0.25 | 0.25 | 0 | 2010-04-15 | 2010-02-26 | https://openmodelica.org:8443/cb/issue/1196
|  | Illegal nested when-statements and when-equations are not detected | Per | Done | 100% | 2 | 0.25 | 0.25 | 0 | 2010-04-15 | 2010-02-26 | https://openmodelica.org:8443/cb/issue/1189
|  | Cleaning old bugs from the bug tracker | Martin | Done | 100% | 4 | 4 | 4 | 0 | 2010-08-20 | 2010-08-20 | Some bugs were fixed; most just closed
|  | Erronous ”Variable not found” error message in EnumTest model | Per | Done | 100% | 2 | 4 | 4 | 0 | 2010-04-29 | 2010-04-15 | https://openmodelica.org:8443/cb/issue/1191
|  | New error message for incorrect tuple assignments | Alexey | Done | 100% | ?? | 1 | 1 | 0 | 2010-12-03 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1322
|  | New error message for recursive short class definitions | Alexey | Done | 100% | ?? | 1 | 1 | 0 | 2010-12-03 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1328
|  | Check for components having the same name as their class | Alexey | Done | 95.24% | ?? | 2.1 | 2 | 0.1 | 2010-12-03 | 2010-02-26
|  | Simulation performance (output formats, filtering) | Martin | Done | 100% | 5 | 5 | 5 | 0 | 2011-03-11 | 2011-03-11
|  | Simulation profiling | Martin | Done | 100% | 10 | 10 | 10 | 0 | 2011-03-11 | 2011-03-11
|  | Check for constant modifications | Alexey | Done | 100% | ?? | 2 | 2 | 0 | 2010-12-03 | 2010-02-26 | http://openmodelica.ida.liu.se:8080/cb/issue/1065
15.0 |  | Cpp code generation / cpp simultion runtime |  |  | 88.94% | 210 | 226 | 201 | 25
|  | simulation runtime for solver,system,event handling, auxiliary classes | Niklas | Done | 94.74% | 80 | 95 | 90 | 5 | 2010-04-19 | 2010-04-19
|  | code generation for dae system, event handling, system porperties | Niklas | Done | 85% | 70 | 100 | 85 | 15 | 2010-04-19 | 2010-04-19
|  | code generation for array, vector, matrices, extern functions, built in functions | Niklas | Done | 75% | 15 | 20 | 15 | 5 | 2010-04-19 | 2010-04-19
|  | make file, vs solution | NIklas | Done | 100% | 10 | 11 | 11 | 0 | 2010-04-19 | 2010-04-19 | dynamic build of simulation
|  | codegneration for algloops,non linear systems, initial value correction | Niklas | Done | ?? | 20 | 0 | 0 | 0 | 2010-04-19 | 2010-04-19
|  | integration in templated code generator | Niklas | Done | ?? | 15 | 0 | 0 | 0 | 2010-04-19 | 2010-04-19

## Increments
Start date | End date | Increment Name | Description
2010-05-24 | 2010-06-15 | i21 | OpenModelica 1.5.0 Release \n – Multibody flattening \n – Interactive simulation\n – CDAC Real-time module\n – Handling structural parameters\n – Record=function equation
2010-06-14 | 2010-07-05 | i24 | OpenModelica 1.5.0 Release \n Media flattening \n Constant evaluation \n QA